## Sheet2
MCI Project Weekly Time Sheet
Team | MB1B | Student ID |  | a1882690 |  | Week starting: | 19/5/2025
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-05-19 | 10:00 | 15:00 | 5 | Add a config-driven switch system (config.py) for toggling data transforms (Sobel, normalization, resolution). | Streamlines experimentation and makes the codebase more modular and extensible for future changes. | Good
Tuesday | 2025-05-20 | 12:00 | 19:00 | 7 | Conduct ablation experiments: compare results with and without Sobel channel, normalized input, and extended negatives. | Identifies key contributors to model performance, informing optimal setup for final deployment. | Good
Wednesday | 2025-05-21 | 12:00 | 17:00 | 5 | Generate comparison plots of mAP, FPS, and confidence histograms for each variant. | Quantifies the trade-off between accuracy and speed in each configuration, supporting balanced model selection. | Good
Thursday | 2025-05-22 | 13:00 | 18:00 | 5 | Finalize and freeze best-performing model checkpoint. Export model weights with version tag. | Ensures reproducibility and clarity in final deliverables, minimizing confusion during later use or integration. | Good
Friday | 2025-05-23 | 13:00 | 18:00 | 5 | Update README with latest inference features, ablation results, and usage instructions. | Completes the packaging of the model for handoff, ensuring others can use and test it independently. | Good
|  |  | Total | 27