## Sheet2
MCI Project Weekly Time Sheet
Team | MB1B | Student ID |  | a1882690 |  | Week starting: | 31/3/2025
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-03-31 | 0:00 | 18:00 | 6 | Perform a comprehensive literature review on unsupervised and weakly supervised learning techniques for object detection. Identify key methods such as Region Contrastive Learning, MIL-based WSOD, and self‑supervised vision transformers. | This review will establish a theoretical foundation for our approach, helping us determine which methods are most promising and define our experimentation framework, thereby guiding the overall strategy for reducing manual annotation. | Good
Tuesday | 2025-04-01 | 15:00 | 22:00 | 7 | Set up the experimental environment and prepare the dataset for unsupervised learning experiments. This includes preprocessing the data and establishing a baseline pipeline using existing supervised techniques for comparison. | The experimental setup is crucial to test unsupervised methods against a supervised baseline, ensuring that subsequent improvements in detection performance can be clearly quantified and aligned with project objectives. | Good
Wednesday | 2025-04-02 | 8:00 | 13:00 | 5 | Implement and test a prototype unsupervised method (e.g., Region Contrastive Learning or MIL-based WSOD) on the prepared dataset. This includes adapting the model architecture and evaluating initial results. | Developing a prototype model will provide practical insights into the strengths and weaknesses of unsupervised approaches, allowing us to refine our methods and integrate these techniques within the overall detection pipeline. | Good
Thursday | 2025-04-03 | 8:00 | 13:00 | 5 | Analyze and compare the performance of the implemented unsupervised method(s) with the supervised baseline. Tune model parameters and refine the algorithm based on quantitative and qualitative evaluations. | The evaluation and tuning phase ensures that our unsupervised models are competitive and robust. This step is key to validating that the new approach can reduce dependency on manual labeling while maintaining detection quality. | Good
Friday | 2025-04-04 | 11:00 | 17:00 | 6 | Integrate the most promising unsupervised learning module into the end-to-end processing pipeline and document the methodology and findings. Prepare a progress report detailing improvements, challenges, and next steps. | Integration and documentation pave the way for full-scale deployment and further research iterations. This task solidifies our progress, aligns the module with the overall project, and sets the stage for subsequent phases in the project plan. | Good
|  |  | Total | 29